## Test Case
List of the improvement scopes | [6 empty] | TEST CASE
1. Full Name field should take only text input or combination of text, numeric. 2. There should be maximum input length in every text field 3.There should be a pick option in password field for visibility of password |  |  |  | Project Name | Meena Bazar |  | PASSED | 81
[7 empty] | FAILED | 10
[7 empty] | Not Executed | 0
[7 empty] | Out of Scope | 0
[7 empty] | TOTAL | 91
TestCase ID | Module | Feature | Test Case | Test Data | Test Steps | Expected Result | Actual Result | Status | Bug Screenshots | Remarks
TC001 | User Management | Sign Up | Verify whether Registration page appears or not |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button | A registration UI should appear | As expected | Passed
TC002 |  |  | Check Grammatical or spelling mistakes on the registration page |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Check whether there are any grammatical or spelling mistakes | No grammatical or spelling mistake should be there | As expected | Passed
TC003 |  |  | Click SignUp button keeping all the mandatory fields blank |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Click on Sign Up button keeping all the fields blank | Error message should appear on every field | As expected | Passed
TC004 |  |  | Check name field keeping empty |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Click on Sign Up button keeping name field blank and other fileds with valid inputs | An error message should appear under name field | As expected | Passed
TC005 |  |  | Check name field entering space inputs |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter multiple spaces in the name field 5. Click on sign up button | It should not accept space inputs | It accepts numerous spaces only as valid input | Failed | Name_Field_Space
TC006 |  |  | Check name field giving numeric inputs only | 12345678910 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter test data in the name field 5. Click on sign up button | It should not accept numeric without alphabets | It accepts numeric data without alphabets as valid input | Failed | Name_Field_Numeic
TC007 |  |  | Check name field giving special characters only | $%^&#####%*! | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter test data in the name field 5. Click on sign up button | It should not accept special characters without alphabets | It accepts special characters without alphabets as valid input | Failed | Name_Field_S_C
TC008 |  |  | Check name field with vaild inputs | Muftain Ahmed Joy | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter test data in the name field 5. Click on sign up button | Name field should accept the input | As expected | Passed
TC009 |  |  | Check whether name field has input max limit | Muftainahmedjoyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyyy | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter test data in the name field 5. Click on sign up button | Name field should have a maximum limit | It takes unlimited input in the name field | Failed | Name_Field_MAX
TC010 |  |  | Check phone number field keeping empty |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Keep the phone number field empty 5. Click on sign up button | An error message should appear under phone number field | As expected | Passed
TC011 |  |  | Check phone number field entering alphabets | myAirtel | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in phone number field 5. Click on sign up button | An error message should appear under phone number field | As expected | Passed
TC012 |  |  | Check phone number field entering alpha-numeric | myAirtel4912 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in phone number field 5. Click on sign up button | An error message should appear under phone number field | As expected | Passed
TC013 |  |  | Check phone number field entering special character | ^&*($! | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in phone number field 5. Click on sign up button | An error message should appear under phone number field | As expected | Passed
TC014 |  |  | Check phone number field entering 10 digits | 0162791491 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in phone number field 5. Click on sign up button | An error message should appear under phone number field | As expected | Passed
TC015 |  |  | Check phone number field entering 12 digits | 016279149122 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in phone number field 5. Click on sign up button | An error message should appear under phone number field | As expected | Passed
TC016 |  |  | Check phone number field entering 11 digits | 01627914912 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in phone number field 5. Click on sign up button | It should accept | As expected | Passed
TC017 |  |  | Check phone number field with a space between valid input | 016279 14912 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in phone number field 5. Click on sign up button | An error message should appear under phone number field | As expected | Passed
TC018 |  |  | Check phone number field with already registered phone number | 1746642733 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in phone number field 5. Click on sign up button | An error message should appear under phone number field telling "Already registered" | As expected | Passed
TC019 |  |  | Check whether verification code is sent or not |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter valid data in phone number field and click on send 5. Click on sign up button | 6 Digit verification code should be sent | As expected | Passed
TC020 |  |  | Check whether verification code is resent or not |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter valid data in phone number field and click on resend 5. Click on sign up button | 6 Digit verification code should be resent after some interval | As expected | Passed
TC021 |  |  | Check verification code field keeping empty |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter valid data in all the field except verification field 5. Click on sign up button | An error message should appear | As expected | Passed
TC022 |  |  | Check verification code field with spaces | 123 45 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter spaces in the verification code field 5. Click on sign up button | An error message should appear | As expected | Passed
TC023 |  |  | Check verification code field with special characters | $#%@#! | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the verification code field 5. Click on sign up button | An error message should appear | As expected | Passed
TC024 |  |  | Check verification code field with alphanumeric inputs | joy123 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the verification code field 5. Click on sign up button | An error message should appear | As expected | Passed
TC025 |  |  | Check verification code field with invalid numeric inputs | 234567 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the verification code field 5. Click on sign up button | An error message should appear | As expected | Passed
TC026 |  |  | Check verification code field with valid numeric inputs | 146987 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the verification code field 5. Click on sign up button | It should accept | As expected | Passed
TC027 |  |  | Check verification code field with less than minimum length pin | 14698 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the verification code field 5. Click on sign up button | An error message should appear | As expected | Passed
TC028 |  |  | Check verification code field with more than maximum length pin | 1469877 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the verification code field 5. Click on sign up button | An error message should appear | As expected | Passed
TC029 |  |  | Check verification code field with expired pin | 145786 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the verification code field 5. Click on sign up button | An error message should appear | As expected | Passed
TC030 |  |  | Check phone number registration without verification |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter valid data in all the fileds keeping the verification code field blank 5. Click on sign up button | An error message should appear | As expected | Passed
TC031 |  |  | Check email field keeping empty |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter valid data in all the fileds except email filed 5. Click on sign up button | It should not show any error message since it is optional field | It's asking to input email | Failed | Email_Optional
TC032 |  |  | Check email field with invalid format | muftain.com | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the email filed 5. Click on sign up button | An error message should appear under email field | As expected | Passed
TC033 |  |  | Check email field with numbers | 1234567332 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the email filed 5. Click on sign up button | An error message should appear under email field | As expected | Passed
TC034 |  |  | Check email field with alphanumeric input without @ sign | muftain1849gmail.com | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the email filed 5. Click on sign up button | An error message should appear under email field | As expected | Passed
TC035 |  |  | Check email field with already registered email | muftain1849@mail7.io | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the email filed 5. Click on sign up button | An error message should appear under email field telling "Already registered" | As expected | Passed
TC036 |  |  | Check email field with valid formats | muftain2022@gmail.com | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the email filed 5. Click on sign up button | It should accept | As expected | Passed
TC037 |  |  | Check email field with multiple spaces |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter multiple spaces in the email filed 5. Click on sign up button | An error message should appear under email field | As expected | Passed
TC038 |  |  | Check password field keeping empty |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter valid data in all the fileds except password filed 5. Click on sign up button | An error message should appear under password field | As expected | Passed
TC039 |  |  | Check password field with alphanumeric inputs | 1213muftain | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the password filed 5. Click on sign up button | Password should be accepted | As expected | Passed
TC040 |  |  | Check password field with special characters | $$$$$$$$@@@@@$ | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the password filed 5. Click on sign up button | Password should be accepted | As expected | Passed
TC041 |  |  | Check password field with numeric inputs only | 2345623412 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the password filed 5. Click on sign up button | Password should be accepted | As expected | Passed
TC042 |  |  | Check password field with upper and lower case alphabets | MuftainAhmed | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the password filed 5. Click on sign up button | Password should be accepted | As expected | Passed
TC043 |  |  | Check password field with multiple spaces |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter multiple spaces in the password filed 5. Click on sign up button | An error message should appear under password field | As expected | Passed
TC044 |  |  | Check whether password field is masked or not |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the password filed 5. Click on sign up button | Written password should be masked | As expected | Passed
TC045 |  |  | Check password field with minimum input length(8) | muftain1 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the password filed 5. Click on sign up button | Password should be accepted | As expected | Passed
TC046 |  |  | Check password field with easily guesable inputs | 12345678 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the password filed 5. Click on sign up button | An error message should appear under password field telling too easy to guess | It did not show any password strength issue | Failed | Easy_Guess_Pass
TC047 |  |  | Check whether password field has maximum input limit or not | 12222222222222222222222222222222233333334fjfdjfhgsjdfgshjfgsjhsgfsjhfgsjfgsdjfgsj | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the password filed 5. Click on sign up button | Password field should have a maximum input limit | It takes unlimited input in the password field | Failed | Unlimited_pass
TC048 |  |  | Check re-enter password field keeping empty |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter valid data in all the fileds except re-type password filed 5. Click on sign up button | An error message should appear under re-enter password field | As expected | Passed
TC049 |  |  | Check re-enter password field with valid alphanumeric inputs | muftain1726 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the re-type password filed 5. Click on sign up button | Password should be accepted | As expected | Passed
TC050 |  |  | Check re-enter password field with valid special characters | *&^&%%$$ | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the re-type password filed 5. Click on sign up button | Password should be accepted | As expected | Passed
TC051 |  |  | Check re-enter password field with valid numeric inputs only | 12348765 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the re-type password filed 5. Click on sign up button | Password should be accepted | As expected | Passed
TC052 |  |  | Check re-enter password field with valid upper and lower case alphabets | MuftainAhnmed | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the re-type password filed 5. Click on sign up button | Password should be accepted | As expected | Passed
TC053 |  |  | Check re-enter password field with spaces |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter multiple spaces in the re-type password filed 5. Click on sign up button | An error message should appear under re-enter password field | As expected | Passed
TC054 |  |  | Check re-enter whether password field is masked or not |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the re-type password filed 5. Click on sign up button | Written password should be masked | As expected | Passed
TC055 |  |  | Check re-enter password field with valid minimum input length(8) | muftain1 | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the re-type password filed 5. Click on sign up button | Password should be accepted | As expected | Passed
TC056 |  |  | Check re-enter password field with valid password | 12348765joy | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the re-type password filed 5. Click on sign up button | Password should be accepted | As expected | Passed
TC057 |  |  | Check whether re-enter password field has maximum input limit or not | 12344joy3333333333333333333333333333333333333333333333333333333333333333333333fdddd | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter the test data in the re-type password filed 5. Click on sign up button | It should have a maximum input limit | It took unlimited input | Failed | Unlimited_re_pass
TC058 |  |  | Check whether "I agree…" checkbox can be checked |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Click on the checkbox "I agree..." 5. Click on sign up button | It should be checked | As expected | Passed
TC059 |  |  | Check whether "I agree…" checkbox can be unchecked |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Click on the checkbox "I agree..." 5. Click on sign up button | It should be unchecked | As expected | Passed
TC060 |  |  | Check whether "I agree…" checkbox is by default unchecked |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Check if "I agree.." is autochecked 5. Click on sign up button | It should be unchecked by default | As expected | Passed
TC061 |  |  | Check whether sign up is possible keeping "I agree…" checkbox unchecked |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter valid data in all the required fields and keep 'I agree..." check box unchecked 5. Click on sign up button | An error should appear to ask for being agreed to terms and conditions | As expected | Passed
TC062 |  |  | Check whether all field name are left alligned or not |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Check all the labelling of the field names 5. Click on sign up button | All field should be left alligned | As expected | Passed
TC063 |  |  | Check clicking "Terms and Conditions" hyperlink |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Click on Terms and Conditions 5. Click on sign up button | It should navigate to the terms and condition page | As expected | Passed
TC064 |  |  | Check Log in hyperlik on sign up form |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Click on Log in displayed on the Sign up page 5. Click on sign up button | It should navigate to the Log in page | As expected | Passed
TC065 |  |  | Check filling all the fields with valid inputs | Full name = Muftain Ahmed Phone = 01746642733 email = muftain1849@mail7.io Pass = 12348765joy | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter valid input to all the fields 5. Click on sign up button | Sign up should be done | As expected | Passed
TC066 |  |  | Check filling all the fields with valid inputs except optional field |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter valid input to all the fields keeping optional field empty 5. Click on sign up button | Sign up should be done | It asked to input email | Failed | Optional_field
TC067 |  |  | Check Facebook API for sign up |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Click on sign up with Facebook 5. Click on sign up button | Should navigate to a FB sign in page if FB ID is signed out previously | As expected | Passed
TC068 |  |  | Check Google API for sign up |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Click on sign up with Google 5. Click on sign up button | Should navigate to a Google sign in page if Google ID is signed out previously | As expected | Passed
TC069 |  | Log in | Check whether Log in page appears |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. Go to log in page | A Log in UI should appear | As expected | Passed
TC070 |  |  | Check grammatical or spelling mistakes on the Log in page |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In 4. Check whether there are any grammatical or spelling mistakes | No grammatical or spelling mistake should be there | As expected | Passed
TC071 |  |  | Check log in keeping all the fields blank |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In button. 4. Keep all the fields blank 5. Click on Log in button | An error message should appear under the relavent fields | As expected | Passed
TC072 |  |  | Check log in with empty email/phone and valid password | Pass = 12348765joy | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In button. 4. Keep email/phone number field empty and enter valid password 5. Click on Log in button | An error should appear | As expected | Passed
TC073 |  |  | Check log in with valid email/phone and empty password | email = muftain1849@mail7.io | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In button. 4. Enter email/phone number field with valid data and keep password field empty 5. Click on Log in button | An error should appear | As expected | Passed
TC074 |  |  | Check log in with valid email and invalid password | email = muftain1849@mail7.io Pass = 12348765joyahmed | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In button. 4. Enter email field with valid data and keep password with invalid data 5. Click on Log in button | An error should appear | As expected | Passed
TC075 |  |  | Check log in with invalid email and valid password | email = muftain1@mail7.io Pass = 12348765joy | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In button. 4. Enter email field with invalid data and keep password with valid data 5. Click on Log in button | An error should appear | As expected | Passed
TC076 |  |  | Check log in with valid email and valid password | email = muftain1849@mail7.io Pass = 12348765joy | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In button. 4. Enter email field with valid data and keep password with valid data 5. Click on Log in button | Log in should be done | As expected | Passed
TC077 |  |  | Check log in with valid phone number and invalid password | Phone = 01746642733 Pass = 12348765joyah | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In button. 4. Enter phone number field with valid data and keep password with invalid data 5. Click on Log in button | An error should appear | As expected | Passed
TC078 |  |  | Check log in with invalid phone number and valid password | Phone = 01746642731 Pass = 12348765joy | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In button. 4. Enter phone number field with invalid data and keep password with valid data 5. Click on Log in button | An error should appear | As expected | Passed
TC079 |  |  | Check log in with valid phone number and valid password | Phone = 01746642733 Pass = 12348765joy | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In button. 4. Enter phone number field with valid data and keep password with valid data 5. Click on Log in button | Log in should be done | As expected | Passed
TC080 |  |  | Check whether password field is masked or not on the log in page |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In button. 4. Enter data in the password field and check whether it is masked 5. Click on Log in button | Written password shoul be masked | As expected | Passed
TC081 |  |  | Check whether password field taking numerous spaces |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In button. 4. Enter numerous spaces in the password field and check whether it is taking these spaces as input 5. Click on Log in button | An error should appear | It took unlimited input and showed valid | Failed | Login_Unlimited_Pass
TC082 |  |  | Check "Can't log in ?" hyperlink |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on ""Log in/ Sign Up "" button. 3. A new page will appear of Log In button. 4. Click on "Can't log in?' button , enter the registered phone number to send OTP and reset password | Should navigate to a recovery password / code page | As expected | Passed
TC083 |  |  | Check whether "Remember me" checkbox can be checked |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on ""Log in/ Sign Up "" button 3. A new page will appear of Log In button 4. Click on "Remember me" checkbox | It should be checked | As expected | Passed
TC084 |  |  | Check whether "Remember me" checkbox can be unchecked |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on ""Log in/ Sign Up "" button 3. A new page will appear of Log In button 4. Click on "Remember me" checkbox to uncheck again | It should be unchecked | As expected | Passed
TC085 |  |  | Check whether "Remember me" checkbox is unchecked by default |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on ""Log in/ Sign Up "" button 3. A new page will appear of Log In button 4. Check "Remember me" checkbox ts unchecked or not | It should be unchecked be default | As expected | Passed
TC086 |  |  | Check "Remember me" feature works when checked |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on ""Log in/ Sign Up "" button 3. A new page will appear of Log In button 4. Fill all the fields with valid input 5. Click remember me checkbox if unchecked. 6. click sign in button 7. After home page appear, close the tab. 8. Go to the url "www.meenabazar.com.bd/login" | Home page should appear | As expected | Passed
TC087 |  |  | Check "Remember me" feature works when unchecked |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on ""Log in/ Sign Up "" button 3. A new page will appear of Log In button 4. Fill all the fields with valid input 5. Click remember me checkbox if checked. 6. click sign in button 7. After home page appear, close the tab. 8. Go to the url "www.meenabazar.com.bd/login" | Sign in UI should appear | As expected | Passed
TC088 |  |  | Check whether all field name are left alligned or not on the log in page |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button 3. A new page will appear of Log In 4. Check all the labelling of the field names | All field should be left alligned | As expected | Passed
TC089 |  |  | Check Facebook API for log in |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on ""Log in/ Sign Up "" button 3. A new page will appear of Log In button 4. Clicking "Facebook" API | Should navigate to a FB sign in page if FB ID is signed out previously | As expected | Passed
TC090 |  |  | Check Google API for log in |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on ""Log in/ Sign Up "" button 3. A new page will appear of Log In button 4. Clicking "Google" API | Should navigate to a Google sign in page if Google ID is signed out previously | As expected | Passed
TC091 |  |  | Check sign up hyperlik on Log in form |  | 1. Go to the url "www.meenabazar.com.bd" 2. Click on ""Log in/ Sign Up "" button 3. A new page will appear of Log In button 4. Click on Sign up button displayed on the Log in page | Sign up page should appear | As expected | Passed

## Test Report
Test Case Report | [5 empty] | Total No. | Status
Project Name | Meena Bazar | Start Date | 2022-11-07 |  |  | 81 | PASS
Module Name | User Management | End Date | 2022-11-11 |  |  | 10 | FAIL
Test Case Version | [5 empty] | 0 | Not Executed
Written By | Muftain Ahmed Joy |  |  |  |  | 0 | Out of Scope
Executed By | Muftain Ahmed Joy
Reviewed By
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 81 | 10 | 0 | 0 | 91
Grand Total | 81 | 10 | 0 | 0 | 91
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
|  |  | Project Name: |  | Meena Bazar
|  |  | Module Name: |  | User Management
|  |  | Reporter Name: |  | Muftain Ahmed Joy
|  |  | Date of creation: |  | 2022-11-07
|  |  | Date of review: |  | DD-MMM-YY
Defect ID | Short description of the bug | Environment | Feature | Build Version | Steps to Reproduce | Status of the Bug | Expected Result | Actual Result | Screenshots | Priority | Severity
D_TC005 | Name field taking inputs of spaces as valid input | Production | Registration | N/A | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter multiple spaces in the name field | New | It should not accept input consist of spaces only | Name field takes inputs consist of just spaces | Name_Space | Low | Minor
D_TC006 | Name field taking inputs of numeric data as valid input | Production | Registration | N/A | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter numeric data in the name field | New | It should not accept input consist of numeric data only | Name field takes inputs consist of just numeric data | Name_Numeric | Low | Minor
D_TC007 | Name field taking inputs of special characters as valid input | Production | Registration | N/A | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter special character in the name field | New | It should not accept input consist of special characters only | Name field takes inputs consist of just special characters | Name_SC | Low | Minor
D_TC009 | Name field takes unlimited input | Production | Registration | N/A | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter unlimited data in the name field | New | It should not accept unlimited data | Name field takes unlimited data | Name-un | Low | Minor
D_TC031 | It's forcing the user to enter email though this field is an optional field | Production | Registration | N/A | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter valid data in all the fileds except email filed 5. Click on sign up button | New | It should allow a user to register without entering email | It is forcing user to provide email to get registered | Email_Optional | High | Critical
D_TC046 | Easily guessable password are taken but no suggestions about strong password | Production | Registration | N/A | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter easy guessable pass in the password filed 5. Click on sign up button | New | It should tell to enter strong password | There is no such suggestion for weak and easily guessable password | Easy_pass | Medium | Major
D_TC047 | Password field taking unlimited data in the input | Production | Registration | N/A | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter unlimited data in the password field 5. Click on sign up button | New | It should not accept unlimited data | Password field taking unlimited data | Unlimited_pass | Low | Minor
D_TC057 | Re-type Password field taking unlimited data in the input | Production | Registration | N/A | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter unlimited data in the re-type password field 5. Click on sign up button | New | It should not accept unlimited data | Re-type Password field taking unlimited data | re_type_un | Low | Minor
D_TC066 | It doesn't let users to register even after fill up the mandatory fields | Production | Registration | N/A | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In and Sign Up button. Click on "Sign Up" button 4. Enter valid input to all the fields keeping optional field empty 5. Click on sign up button | New | It should let users get registered if they enter vaid data in the mandatory fields | It doesn't let users to register asking to fill up the optional field also | Optional | Low | Minor
D_TC081 | Password field on the log in page takes unlimited input | Production | Log in | N/A | 1. Go to the url "www.meenabazar.com.bd" 2. Click on "Log in/ Sign Up " button. 3. A new page will appear of Log In button. 4. Enter numerous spaces in the password field and check whether it is taking these spaces as input 5. Click on Log in button | New | It should not accept unlimited data | Password field taking unlimited data | login_pass_unlimited | Low | Minor

## Test Metrics
SL | Required Data |  | Metrics | Formula | Result in %
1 | No of Requirements |  | % of test case executed | (No of test cases executed / total no of test cases written)*100 | 100
2 | Avg. No. of Test Cases written per requirements |  | % of test cases not executed | (No of test cases not executed/total no of test cases written)*100 | 0
3 | Total no of test cases written for all requirements | 91 | % of test cases passed | (No of test cases passed/total test cases executed)*100 | 89
4 | Total no of test case executed | 91 | % of test cases failed | (No of test cases failed/total test cases executed)*100 | 11
5 | No of test cases passed | 81 | % of test cases blocked | (No of test cases blocked/total test cases executed)*100 | 0
6 | No of test case failed | 10 | Defect density | (No of defects found/no of requirements)*100
7 | No of test cases blocked | 0 | Defect Removal Efficiency (DRE) in % | ( Defects identified during testing/ (defects identified during testing + defects identified by customers))*100
8 | No of test cases unexecuted |  | Defect Leakage in % | (No of defects found in UAT/no of defects found in testing)*100
9 | Total no of defects identified | 10 | Defect Rejection Ratio in % | (No of defect rejected/ total no of defects raised)*100
10 | Critical defects count
11 | Higher defects count
12 | Medium defects count
13 | Low defects count
14 | Customer defects |  | Defect Age | Fixed date-Reported date
15 | No of defects found in UAT |  | Customer satisfaction | No of complaints per period of time